## MME
Time | Summary | Estimate time(hours) | Owner | Status | Real Working hours | Comment
10.8-10.14 | 1.[Bug] GCS-xxx:<sqa>:<>:<>: doesnot reply with Forward Relocation Response when doesnot discover a . | 40 | ChenYi |  | 40 | 1.[其它] GCS-xxx:Merge master tracing into release2.1 - Status: Complete 2.[Bug] GCS-xxx:AMF doesnot reply with Forward Relocation Response when doesnot discover a . - Status: In progress - Progress: Find that can't register to nrf with now. Related smf bug id are GCS-11404 and GCS-xxx
| 1.[Bug] GCS-: 2.[Bug] GCS-:kpi issues | 40 | HeEr |  | 40 | 1.[Bug] GCS-: alarms Http.SmContextsPost - Status: Fixed 2.[Bug] GCS-: count "SmContextPosts" statusCode - Status: Fixed 3.[Bug] GCS-: grafana dashboard displays Uecm Registration Success Rate panel - Status: In progress - Progress: Wating to be reviewed & merged 4.[Bug] GCS-:Target AMF support security algorithm update in Mobility Registration Update Procedure - Status: In progress - Progress: Coding 5.[其它] write doc 《探索 PromQL》 - Status: Complete - Progress: http:///zh/k8s/prometheus/%E6%8E%A2%E7%B4%A2Promql 6.[其它] write doc 《Prometheus 告警处理》 - Status: Complete - Progress: http:///zh/k8s/prometheus/prometheus%E5%91%8A%E8%AD%A6%E5%A4%84%E7%90%86 7.[其它] write doc 《分析 CASA alert 规则》 - Status: Complete - Progress: http:///zh/k8s/prometheus/%E5%88%86%E6%9E%90Casa-Alert%E8%A7%84%E5%88%99
| 1.On vacation | 40 | xxx |  | 40 | 1.[Feature] GCS-: should support S6B in 3GPP Access to Untrusted Non-3GPP IP Access Handover with GTP on S2b - Status: In progress - Progress: Finish codeing without trace. Finish test by smf-tester. Waiting for merge 2.[Feature] GCS-:AAA-Client should support to handle s6b AAR and AAA for claro - Status: In progress - Progress: Finish codeing. Finish test by smf-tester. Waiting for merge
| 1.[Bug] GCS-:<sqa>:<>:<>: should set the rat type as NR during EPS to 5G handover. | 40 | xxx |  | 40 | 1.[Bug] GCS-: should set the rat type as NR during EPS to 5G handover. - Status: Complete 2.[Bug] GCS-: does not reply the "reportList" in rsp message after receiving modify subscription event request with immediateFlag attribute set to true. - Status: In progress - Progress: Testing
| 1.[Feature] GCS-:gtpp dictionary custom24 | 40 | xxx |  | 40 | 1.[Bug] GCS-:gtpp dictionary custom24 - Status: In progress - Progress: code: finish test: 90% review: working
| 1.[Study] ppt-sharing & maybe other work | 40 | xxx |  | 40 | 1.[Study] Continue on learning k8s and operator, then do the learning&sharing. - Status: Complete 2.[Study] Learn code of sctpmgr, n2mgr and understand how they interact by grpc. - Status: Complete
| 1.[Study] do a presentation about premetheus and grafana. | 40 | xxx |  | 40 | 1.[Study] Do a presentation about premetheus and grafana. - Status: Complete 2.[Study] Read the code of n2mgr and sctpmgr. - Status: In progress
| 1.[Bug] FGC-:YTL testing, DCNR feature. | 40 | xxx |  | 40 | 1.[Bug] FGC-: IVC: Issue with 'show mme statistics slg-interface diameter verbose' - Status: Fixed 2.[Bug] FGC-:MME shall set the UE sessions as idle state if the sctp association has been aborted - Status: Close 3.[Bug] FGC-:If there is a DCN for ue, MME should select PGW using ue-usage-type. - Status: In progress - Progress: Met other issue during the self test 4.[Study] Add 3 MME function description documents to confluence. - Status: Complete
10.17-10.21 | 1.[Bug] GCS-: 2.[Bug] GCS-: | 40 | ChenYi
| 1.[Bug] GCS-: | 40 | HeEr
| 1.[Feature] GCS-:Finish tracce part and new a tc. | 40 | xxx
| 1.[Bug] GCS-: does not reply the "reportList" in rsp message after receiving modify subscription event request with immediateFlag attribute set to true. | 40 | xxx
| 1.[Bug] GCS-: | 40 | xxx
| 1.[Bug] GCS-: log info "Ignoring event NgapUeRadioCapabilityInfoIndication received in state Idle, procedure ServiceRequestProcedure". | 40 | xxx
| 1.[Bug] GCS-: send duplicate subscription to | 40 | xxx
| 1.[Bug] FGC-:If there is a DCN for ue, should select PGW using ue-usage-type. 2.[Bug] FGC-: /0 crash exit-code 139 on version 1.6.44. | 40 | SunJianHua