## MME
Time | Summary | Estimate time(hours) | Owner | Status | Real Working hours | Comment
10.8-10.14 | 1.[Bug] GCS-10696:<sqa>:<amf>:<uemgr>: AMF doesnot reply mme with Forward Relocation Response when doesnot discover a smf. | 40 | ChenJianDe |  | 40 | 1.[其它] GCS-10168:Merge master tracing into release2.1 - Status: Complete 2.[Bug] GCS-10696:AMF doesnot reply mme with Forward Relocation Response when doesnot discover a smf. - Status: In progress - Progress: Find that smf can't register to nrf with pgwFQDN now. Related smf bug id are GCS-11404 and GCS-10378
| 1.[Bug] GCS-10413: 2.[Bug] GCS-10521:kpi issues | 40 | HeNuanFen |  | 40 | 1.[Bug] GCS-11117:AMF alarms Http.SmContextsPost - Status: Fixed 2.[Bug] GCS-11118:AMF count "SmContextPosts" statusCode - Status: Fixed 3.[Bug] GCS-10575: grafana dashboard displays Uecm Registration Success Rate panel - Status: In progress - Progress: Wating to be reviewed & merged 4.[Bug] GCS-10413:Target AMF support security algorithm update in Mobility Registration Update Procedure - Status: In progress - Progress: Coding 5.[其它] write doc 《探索 PromQL》 - Status: Complete - Progress: http://172.0.15.220/zh/k8s/prometheus/%E6%8E%A2%E7%B4%A2Promql 6.[其它] write doc 《Prometheus 告警处理》 - Status: Complete - Progress: http://172.0.15.220/zh/k8s/prometheus/prometheus%E5%91%8A%E8%AD%A6%E5%A4%84%E7%90%86 7.[其它] write doc 《分析 CASA alert 规则》 - Status: Complete - Progress: http://172.0.15.220/zh/k8s/prometheus/%E5%88%86%E6%9E%90Casa-Alert%E8%A7%84%E5%88%99
| 1.On vacation | 40 | LiMingEn |  | 40 | 1.[Feature] GCS-11066:SMF should support S6B in 3GPP Access to Untrusted Non-3GPP IP Access Handover with GTP on S2b - Status: In progress - Progress: Finish codeing without trace. Finish test by smf-tester. Waiting for merge 2.[Feature] GCS-11136:AAA-Client should support to handle s6b AAR and AAA for claro - Status: In progress - Progress: Finish codeing. Finish test by smf-tester. Waiting for merge
| 1.[Bug] GCS-11042:<sqa>:<amf>:<uemgr>: AMF should set the rat type as NR during EPS to 5G handover. | 40 | CuiMingShu |  | 40 | 1.[Bug] GCS-11042:AMF should set the rat type as NR during EPS to 5G handover. - Status: Complete 2.[Bug] GCS-11077:AMF does not reply the "reportList" in rsp message after receiving modify subscription event request with immediateFlag attribute set to true. - Status: In progress - Progress: Testing
| 1.[Feature] GCS-10613:gtpp dictionary custom24 | 40 | MaZhenFeng |  | 40 | 1.[Bug] GCS-10613:gtpp dictionary custom24 - Status: In progress - Progress: code: finish test: 90% review: working
| 1.[Study] ppt-sharing & maybe other work | 40 | ChenJiaWen |  | 40 | 1.[Study] Continue on learning k8s and operator, then do the learning&sharing. - Status: Complete 2.[Study] Learn code of sctpmgr, n2mgr and understand how they interact by grpc. - Status: Complete
| 1.[Study] do a presentation about premetheus and grafana. | 40 | ZhongRongBin |  | 40 | 1.[Study] Do a presentation about premetheus and grafana. - Status: Complete 2.[Study] Read the code of n2mgr and sctpmgr. - Status: In progress
| 1.[Bug] FGC-3085:YTL testing, DCNR feature. | 40 | SunJianHua |  | 40 | 1.[Bug] FGC-2958: IVC: Issue with 'show mme statistics slg-interface diameter verbose' - Status: Fixed 2.[Bug] FGC-3095:MME shall set the UE sessions as idle state if the sctp association has been aborted - Status: Close 3.[Bug] FGC-3016:If there is a DCN for ue, MME should select PGW using ue-usage-type. - Status: In progress - Progress: Met other issue during the self test 4.[Study] Add 3 MME function description documents to confluence. - Status: Complete
10.17-10.21 | 1.[Bug] GCS-10696: 2.[Bug] GCS-10984: | 40 | ChenJianDe
| 1.[Bug] GCS-10413: | 40 | HeNuanFen
| 1.[Feature] GCS-11066:Finish tracce part and new a tc. | 40 | LiMingEn
| 1.[Bug] GCS-11077:AMF does not reply the "reportList" in rsp message after receiving modify subscription event request with immediateFlag attribute set to true. | 40 | CuiMingShu
| 1.[Bug] GCS-10613:https://jira.casa-systems.com/browse/GCS-10613 | 40 | MaZhenFeng
| 1.[Bug] GCS-11382: log info "Ignoring event NgapUeRadioCapabilityInfoIndication received in state Idle, procedure ServiceRequestProcedure". | 40 | ChenJiaWen
| 1.[Bug] GCS-11369: AMF send duplicate subscription to NRF | 40 | ZhongRongBin
| 1.[Bug] FGC-3016:If there is a DCN for ue, MME should select PGW using ue-usage-type. 2.[Bug] FGC-3099:MME connmgr/0 crash exit-code 139 on MME version 1.6.44. | 40 | SunJianHua